## Slide 1
MINISTRY OF TRADE, INDUSTRY AND COOPERATIVES
Uganda-UNIDO Programme for Country Partnership (PCP)
Inception Report
Iron & Steel · Copper & Allied Metals · Automotive Value Chains
1. Iron & Steel
2. Copper & Allied Metals
3. Automotives
Solomon Ariho | 27 May 2026 | Draft — for TWG review

## Slide 2
Section 1
Introduction

## Slide 3
Study Overview
This Inception Report covers three priority value chains designated under NDP IV:
1. Iron & Steel
2. Copper & Allied Metals
3. Automotives
Together, these chains represent Uganda's most significant opportunity for mineral-based industrialization —
anchored in the country's iron ore and copper resource endowments and the strategic push toward
domestic vehicle manufacturing through Kiira Motors Corporation.
This document sets out the study design and workplan, diagnostic framework, data plan,
stakeholder consultation approach, and prioritization methodology.

## Slide 4
Section 2
Study Design & Workplan

## Slide 5
Report Structure
Chapter | Title
1 | Executive Summary (written last)
2 | Background and Policy Context
3 | Methodology and Analytical Framework
4 | Iron & Steel Value Chain
5 | Copper & Allied Metals Value Chain
6 | Automotive Value Chain
7 | Cross-Cutting Priority Actions and Policy Recommendations
8 | Investment Portfolio and Implementation Roadmap

## Slide 6
Workplan and Timeline
Task | Target Date
Inception Report submitted for TWG review | 29 May 2026
TWG approval of Inception Report | 31 May 2026
Chapter 2: Background and Policy Context | 31 May 2026
Chapter 3: Methodology and Analytical Framework | 1 June 2026
Chapter 4: Iron & Steel — draft | 2 June 2026
Chapter 5: Copper & Allied Metals — draft | 3 June 2026
Chapter 6: Automotive — draft | 4 June 2026
Chapter 7: Cross-cutting recommendations | 5 June 2026
Chapter 8: Investment portfolio and roadmap | 6 June 2026
Chapter 1: Executive Summary | 7 June 2026
Final report submitted to MTIC | 8 June 2026

## Slide 7
Schedule — Gantt Chart
May 29
May 31
Jun 1
Jun 2
Jun 3
Jun 4
Jun 5
Jun 6
Jun 7
Jun 8
Inception Report draft
TWG approval
Ch2 Background & Policy
Ch3 Methodology
Ch4 Iron & Steel
Ch5 Copper & Allied Metals
Ch6 Automotive
Ch7 Cross-cutting
Ch8 Investment Roadmap
Ch1 Executive Summary
Final submission

## Slide 8
Section 3
Diagnostic Framework
Six-part template applied across all three chains

## Slide 9
Analytical Framework — Six Parts
Part A — Value Chain Map
Full mapping from primary inputs to all end products. Identifies where Uganda currently participates,
where value is lost, and where import substitution and export opportunities exist.
Part B — Current State Assessment
Production volumes, firms, employment, capacity utilization, export and import values.
Part C — Binding Constraints Analysis
Ten dimensions: inputs, technology, energy, water, logistics, waste management,
finance, skills, standards, and policy/regulatory environment.
Part D — Market Assessment
Domestic, regional (EAC/COMESA), and global markets.
Part E — Prioritized Products
3–4 products per chain selected via the scoring framework. Explicit deprioritization with rationale.
Part F — Priority Action Matrix
Quick wins (0–12 months) · Policy reforms (1–3 years) · Investment interventions (3–5 years)

## Slide 10
Section 4
Data Plan

## Slide 11
Primary Data Sources
Value Chain | Primary Sources
Iron & Steel | NPA/UDC Report on the Mapping and Value Chain Analysis (June 2025); KIIs with 40 steel firms, 5 mining players, 9 MDAs
Copper & Allied Metals | KIIs with copper wire/cable manufacturers; UNMC on Kilembe mine; MEMD on copper reserves and licenses
Automotives | KIIs with Kiira Motors Corporation (KMC); bus body fabricators; spare parts manufacturers; MWT on vehicle import data

## Slide 12
Data Gaps and Mitigation
Gap | Chain | Mitigation
Firm-level production data for copper processors | Copper & Allied Metals | KIIs with UMA member firms; URA HS code trade data as proxy
Copper reserve quantity and grade data | Copper & Allied Metals | MEMD consultation; UNMC data on Kilembe
Automotive assembly and body fabrication capacity | Automotives | KIIs with KMC and private assemblers; URA vehicle import HS codes
Regional copper and automotive market sizing | Both | UN Comtrade; ITC Trade Map; African Development Bank sector reports

## Slide 13
Section 5
Stakeholder Consultation Plan

## Slide 14
Key Informant Interviews (KIIs)
Stakeholder Category | Institutions / Firms | Chain(s)
Public sector | MTIC, UIA, URA, UBOS, UNBS, UEPB, MEMD, UNMC, KMC, MWT | All
Private sector — Iron & Steel | 40 steel firms, SINO Minerals, Tembo Steel, Abyssinia Iron & Steel, Roofings Ltd, Steel & Tube, Uganda Baati | Iron & Steel
Private sector — Copper | Copper wire/cable manufacturers; scrap copper processors; construction materials importers | Copper & Allied Metals
Private sector — Automotive | KMC; bus body fabricators; spare parts manufacturers and importers | Automotives
Industry associations | Uganda Manufacturers Association (UMA) | All
Financial Institutions | Uganda Development Bank (UDB), Uganda Development Corporation (UDC), East African Development Bank (EADB), commercial banks | All
Research / academia | Makerere University (engineering, materials science), UIRI | All

## Slide 15
Validation Workshop
A structured stakeholder validation workshop will be held before the report is finalized.
The workshop will:
· Present draft prioritization findings for each of the three value chains
· Test priority product selections and action matrices against stakeholder knowledge
· Identify material gaps or contested findings
· Produce agreed outputs reflected in the final report
Proposed timing: Week of 2–6 June 2026
(after chapter drafts are complete, before final submission)
Proposed participants: TWG members · Private sector representatives · MTIC · UIA · UNBS · UDB
and relevant development partners

## Slide 16
Section 6
Prioritization Methodology

## Slide 17
Scoring Framework — Five Criteria
# | Criterion | Description | Weight
1 | Accessible market size | Size and growth rate of domestic, regional, and export market Uganda can realistically access | 25%
2 | Uganda's comparative advantage | Availability of raw material inputs, existing productive base, geographic proximity to key markets | 25%
3 | Feasibility | Capital requirements, technology readiness, lead time to commercial scale, management capability | 20%
4 | Job creation and income potential | Direct and indirect employment, wage levels, upstream and downstream linkage effects | 15%
5 | Import substitution impact | Value of current imports that domestic production could displace; current account benefit | 15%

## Slide 18
Scoring Scale and Interpretation
Score | Meaning
5 | Excellent — strong evidence of competitive advantage or large accessible market
4 | Good — solid case with manageable constraints
3 | Moderate — feasible but with significant constraints to address
2 | Weak — limited advantage or small market; would require disproportionate investment
1 | Poor — Uganda has no realistic competitive position; not recommended

## Slide 19
Analytical Principle
Successful countries are known for three or four products.
The economies are built around those few.
Uganda must not try to do everything.
Composite score = sum of (criterion score × criterion weight) across all five criteria.
· Above 3.5 → Priority product
· 2.5 – 3.5 → Conditional priority (subject to enabling conditions)
· Below 2.5 → Explicitly deprioritized with rationale
The output of this study is a focused prioritization, not a catalogue.
Every chain analysis must conclude with a clear statement of what Uganda should do
— and what it should NOT do — at this stage.

## Slide 20
Section 7
Request for TWG Approval

## Slide 21
TWG is Requested to:
1. Confirm the study scope, diagnostic framework, and assessment templates (Section 3)
2. Confirm or revise the prioritization criteria and weights (Section 6)
3. Approve the workplan and timeline in Section 2,
including the 8 June 2026 final submission deadline
4. Provide any additional guidance before chapter drafting commences
Upon TWG approval, chapter drafting will proceed in accordance with the workplan.
The TWG will be kept informed of progress and any material data gaps as they arise.